## User_Stories
ID | Story Title | Depends On | Points | Priority | As a/an [user type] | I want [functionality] | So that [value] | NFR | Definition of Done | Epic ID | Notes | Status
S1 | Appointment Slot |  | 5 | high | Client | to view and selecting available appointment slots | I can find which times work best me |  | When clients can view available/unavailable times | 1 |  | Open
S2 | Booking Confirmation |  | 5 | high | Client | to receive confirmations | I am assured my appointment has been set |  | When clients receive a confirmation shortly after scheduling an appointment | 1 | Need to send confirmation code for later reference | Open
S3 | Reminder |  | 2 | high | Client | to receive reminders | I don’t forget my appointments |  | When cleints receive a reminder before their appointment | 1 |  | Open
S4 | Cancel appointment |  | 2 | high | Client | to cancel my appointment | I can accommodate schedule changes |  | When clients can cancel appointments on their own | 1 |  | Open
S5 | Reschedule |  | 3 | high | Client | to reschedule my appointment | I can accommodate schedule changes |  | When clients can reschedule appointments on their own | 1 |  | Open
Open
S6 | Browse services |  | 5 | high | Client | to browse detailed descriptions and pricings for services | I can select the service that best fits my needs |  | When clients can explore all the provided service options | 2 | Code this page in such a way that the admin will be able to modify its contents later without coding | Open
S7 | Browse Past work |  | 5 | high | Client | to browse previous work through images/videos | I can assess the quality of services before booking |  | When clients can properly judge the quality of past work | 2 | Code this page in such a way that the admin will be able to modify its contents later without coding | Open
Open
S8 | Contact |  | 3 | med | Client | a contact form | I can ask questions or request more information |  | When clients can easily contact the business directly | 3 |  | Open
S9 | Testimonials |  | 1 | med | Client | to read testimonials and reviews from other clients | I can further trust the quality and professionalism of the business |  | When clients can browse what previous clients had to say | 3 |  | Open
S10 | Instagram Feed Integreation |  | 5 | med | Client | to view the business's instagram feed | I can stay updated on their latest work |  | When clients can view the instagram feed from the website | 3 | learn ig api? | Open
Open
S11 | Admin account |  | 3 | high | Admin | secure admin login credentials | only authorized users can make content changes on the website |  | When the admin can securely login | 4 |  | Open
S12 | Admin Edit Portfolio |  | 8 | high | Admin | to add, edit, or delete portfolio images easily | I can keep my portfolio up to date and attract new clients |  | When the admin can change the images available for clients to browse | 4 |  | Open
S13 | Update services |  | 8 | high | Admin | to update service descriptions and pricing | I can keep the services available up to date |  | When the admin can make changes to descriptions and pricings without coding | 4 |  | Open
S14 | Modify timeslots |  | 5 | high | Admin | to define which times are available for appointments | I can maintain control over the scheduling process |  | When the admin can update their availability | 4 |  | Open
S15 | View scheduled appointments |  | 3 | high | Admin | to view a list of all scheduled appointments for the day | I can easily keep track of what appointments remain |  | When the admin can view the schedule after logging in | 4 |  | Open
63
NFR Usability
Interface shall be mobile-responsive
Website shall be accessible on major browsers (Chrome, Firefox, Safari)
NFR Security
Admin access shall require secure authentication
NFR Reliability
System shall have steady uptime
NFR UI
The system will maintain a constant monochrome colorscheme

## Classes
Class:
Knows:
Knows:
Knows:
Knows:
Knows:

## Tasks
ID | Task Title | Task Description | Story ID

## Epics
ID | Epic Title | Description